# LLM-Based Log Analysis Prototype – 4–6 Week Implementation Plan

LLM-Based Log Analysis Prototype – 4–6 Week Implementation Plan

Goal
Build a small prototype where a support engineer pastes logs and the system retrieves related code and dependency context to generate:
- Incident summary
- Probable root cause (RCA)
- Cause category
- Suggested next steps

This is NOT an enterprise product initially. The objective is a reliable investigation assistant for a small team/service.

Target Outcome (End of 4–6 Weeks)

User pastes logs
→ Log parser extracts signals
→ Retrieve related code chunks from vector DB
→ Retrieve dependency context
→ Build evidence pack
→ LLM generates RCA and suggestions

Simple CLI or minimal web UI is sufficient.

Simplified Prototype Architecture

Logs Input
→ Parser
→ Retriever (code + docs)
→ Vector DB
→ Prompt Builder
→ LLM
→ RCA Output

Suggested Tools
Language: Python
Embeddings: OpenAI or similar
Vector DB: FAISS or Chroma
Code ingestion: GitHub API
UI: CLI or Streamlit

Team Role Split (3 Members)

Person 1 – Data & Chunking
Responsibilities:
- GitHub repo ingestion
- Code chunking
- Embedding generation
- Vector DB indexing

Person 2 – Log Analysis
Responsibilities:
- Log parsing
- Extracting signals
- Building incident context
- Dependency matching

Person 3 – LLM & RCA
Responsibilities:
- Prompt design
- Evidence pack creation
- RCA output format
- Suggestion generation

WEEK 1 – Pipeline Understanding and Code Ingestion

Deliverable: Vector DB containing code chunks.

Person 1 – Code Ingestion
Tasks:
- Clone GitHub repository
- Read all source files
- Chunk code by function/method
- Store chunks with metadata

Example chunk:
service: order-service
file: PaymentClient.java
method: processPayment
code: <method body>

Generate embeddings and store in vector DB.

Person 2 – Log Dataset
Collect real log samples and store small dataset:

incident_1_logs.txt
incident_2_logs.txt
incident_3_logs.txt

Extract fields:
timestamp
service
class
exception
dependency

Begin building log parser.

Person 3 – Prompt Prototype
Design structured output:

INCIDENT SUMMARY
ROOT CAUSE CATEGORY
LIKELY ROOT CASE
EVIDENCE
SUGGESTED NEXT STEPS

Test simple prompts using manual input.

WEEK 2 – Log to Code Retrieval

Deliverable: Paste log → retrieve relevant code.

Person 1
Improve chunk metadata:

class
method
repo
service

Add keyword index.

Person 2
Enhance log parser to extract:

exception
class name
method
dependency name

Example:
NullPointerException at OrderService.processOrder

Convert extracted fields into search query.

Person 3
Build retrieval logic:

query = extracted error + class name
vector search → top 5 chunks

Print retrieved code.

WEEK 3 – Dependency Awareness

Deliverable: System understands downstream services.

Create dependency file example:

order-service → payment-service
order-service → inventory-service
payment-service → bank-api

Store as JSON.

Person 2
Enhance parser to detect:

timeout
connection refused
HTTP 500

Map signals to:

infra
downstream
code

Person 3
Add basic RCA classification rules:

timeout + dependency → downstream
NullPointerException → code
DB connection failure → infra

LLM will refine classification later.

WEEK 4 – RAG Pipeline

Deliverable: System generates RCA.

Pipeline:

logs
→ parse
→ retrieve code chunks
→ build evidence
→ LLM call
→ RCA output

Example prompt:

You are a production incident investigator.

Logs:
{log chunk}

Relevant code:
{code chunk}

Dependency map:
{dependency}

Determine:
1) incident summary
2) probable root cause
3) category (code/data/infra/downstream)
4) suggested next checks

WEEK 5 – Reliability Improvements (Optional)

Add:
Evidence references

Example:
Evidence:
- log line 32
- PaymentClient.java line 84

Add confidence scoring:

confidence: medium

Add suggestion engine:

Check PaymentClient timeout configuration
Verify payment-service health
Inspect null handling in OrderService.processOrder

WEEK 6 – Simple UI (Optional)

Use Streamlit.

User flow:
paste logs → click analyze

Output displays:
Incident Summary
RCA
Evidence
Suggestions

High-Level Prototype Flow

Logs
→ Log Parser
→ Signal Extractor (service, error, dependency)
→ Retriever (vector search)
→ Evidence Pack (log + code + dependency)
→ LLM
→ RCA + Suggestions

What NOT to Build Initially

- Infra metrics ingestion
- Distributed tracing
- Large dependency graphs
- Enterprise authentication
- Automated log ingestion
- CI/CD integrations
- Model fine-tuning

These can be added later.

Success Criteria

Prototype successful if support engineer can paste logs and receive:

Incident Summary
Likely Root Cause
Category
Evidence
Next Steps

Even 60–70% accuracy is acceptable for phase one.

Key Principle

Do not rely entirely on LLM intelligence.

Most intelligence should come from:
- log parsing
- dependency mapping
- retrieval quality

LLM responsibilities:
- reasoning
- explanation
- summarization

Example User Experience

Input:

NullPointerException at OrderService.processOrder
Error while calling PaymentClient
TimeoutException

Output:

Incident Summary
Order processing failed due to payment dependency timeout.

Root Cause Category
Downstream dependency

Likely Cause
Payment service timeout while OrderService was calling PaymentClient.processPayment.

Evidence
- TimeoutException in logs
- Code call from OrderService → PaymentClient
- Dependency map showing payment-service

Suggested Checks
1) Verify payment-service health
2) Check timeout configuration
3) Review PaymentClient retry settings